## Slide 1
Date Range | Blockchain & Chaincode Developer | Web Developer | AI/ML Developer
Aug 1 – 7 | - Project kickoff, finalize specs and workflows | - Setup project repo, dev environment | - Research data/input requirements for bid evaluation
 | - Deploy Minifab-based Fabric test network | - Basic UI mockups for RFQ & bids | 
Aug 6 – 13 | - Start writing chaincode for RFQ management | - Begin API development for blockchain interaction | - Start AI model prototype development (basic scoring)
Aug 14 – 19 | - Complete chaincode for RFQ, bid submission & compliance | - Develop bid submission, off-chain doc upload UI | - Refine AI model, integrate bid evaluation logic
 | - Test chaincode functions locally | - Backend integration with blockchain network | - Test AI scoring using sample bid data
Aug 20 – 25 | - Chaincode enhancements and bug fixes | - Build dashboards for owner, contractors, PM | - Integrate AI module to accept on-chain references and documents metadata
 | - Implement smart contract APIs for frontend | - Implement authentication and role-based access | - Develop API/service to send AI scores back on-chain
Aug 26 – 28 | - Finalize and deploy tested chaincode | - Frontend UI polishing and responsiveness improvements | - Complete AI evaluation module, prepare batch processing
 | - Support integration testing | - Connect smart contract event listeners for UI notifications | - Validate AI output with blockchain workflow
Aug 29 – 30 | - End-to-end testing of chaincode + blockchain APIs | - Complete full workflow UI (+ bid alerts, results) | - End-to-end test of AI model feedback loop with blockchain
Aug 31 – Sept 9 | - Support final testing & bug fixing | - Final UI/UX tweaks based on feedback | - Assist AI-related fine tuning and demo scripts
 | - Prepare deployment scripts & documentation | - Prepare demo environment and walkthroughs | - Prepare explanation and demo of AI evaluation logic

## Slide 2
1. RFQ Creation
Owner creates a Request for Quotation (RFQ) on the platform.
SCOPE, DEADLINES, CRITERIA are immutably recorded on-chain.
2. Bid Alert
PM using Platform sends notifications to all pre-registered and eligible contractors about the new RFQ.
Contractors receive these alerts via dashboard messages and/or email, ensuring timely awareness of bidding opportunities.
3. Bid Preparation & Submission
Each contractor prepares their bid, uploading required documents to secure off-chain storage.
For every bid, a secure reference (hash or link) to the off-chain documents, along with key bid data (price, timeline, qualifications), is submitted on-chain before the deadline.
4. Compliance Check & Bid Closure
Smart contract verifies each submission for basic compliance (deadline met, required docs referenced).
Submission window automatically closes at the set deadline; on-chain logs freeze the accepted bids.
5. AI-Powered Bid Evaluation
AI module works off-chain, analyzing all on-chain references and off-chain documents.
Bid scores or rankings are provided to the smart contract.
6. Winner Selection & Announcement
Smart contract applies predefined rules and AI results to select the best bid. With PM involved
Winner notification and selection records are immutably logged on-chain.
7. Project Execution & Milestone Submission
Contractor delivers work according to project plan, uploading milestone evidence off-chain and submitting its hash on-chain.
8. Milestone Verification & Payment
Owner reviews milestone proofs.
Smart contract releases payments on-chain for approved milestones.
9. Auditing and Oversight
All events are recorded on-chain for transparency.
Auditors review on-chain records and, as authorized, access detailed off-chain documentation under strict permissions.